## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Setup project | 0.5 | 13/12/2024 | Setup project, dependencies, updating SDK, converting logo to svg for better quality
User story 1: Create draftUI, splash screen | 2 | 13/12/2024 | Create AppColor helper, create draft UI, images and icons.
User story 2: Api client, Home Page | 2 | 13/12/2024 | Api client(checking API), Home page
User story 2: BottomNavigation, search. | 0.5 | 14/12/2024 | Search empty state (UI), User location, search
User story 2: Bloc Provider | 5 | 14/12/2024 | Add Bloc, setup
User story 2: Add fonts | 1 | 15/12/2024 | Add fonts helper, color helper, image helper
User story 3: Detail Page | 1 | 15/12/2024 | Detail screen UI
User story 3: Map and location | 3 | 15/12/2024 | Working with map, user location, permission
User story 4: About Page | 1 | 16/12/2024 | About page UI
Refactoring code | 3 | 16/12/2024 | reactoring code, renaming, optimization code. Fixing UI
Wishlist page | 1 | 17/12/2024 | Wishlist page UI
Wishlist page business logic | 4 | 17/12/2024 | add functionality to make house favorite on detail screen. And show it on Wishlist Page
hero animation, no internet state | 1 | 17/12/2024 | Hero animation, handle no internet state
Store data if no internet | 3 | 18/12/2024 | Store data(Hive) if no internet, cache the response from the database
Dark/light mode | 2 | 18/12/2024 | Dark mode support
Settings page | 1 | 18/12/2024 | Settings page UI
Localization | 2 | 18/12/2024 | Support localization(Dutch language)
Improve UI | 1 | 18/12/2024 | Move About page to Settings page.
Polishing | 1 | 19/12/2024 | Refactoring, UI, fixing bugs, improve perfomance and etc.
Total amount of hours | 35